# AIQL ERP — 6-Month Development Plan

Hand to Sonnet one day at a time. Each day is a focused, self-contained deliverable.

Table of Contents

# AIQL ERP — 6-Month Day-by-Day Development Plan

Total: 130 working days across 4 phases Pace assumption: 5 productive engineering days/week, ~6-7 hours each Used with: Claude Sonnet for execution; this human reviews and approves

# How to Use This Plan

## The daily workflow

Each day's entry has 6 sections:

- Objective — One sentence: what done looks like

- Files — Specific paths to create or modify

- Implementation notes — Architecture / approach guidance

- Tests — What must pass before "done"

- Acceptance criteria — Checklist for verification

- Sonnet prompt — Copy-paste this into a fresh Sonnet session

## The Sonnet prompt pattern

Each prompt includes:

- A "Read first" list of files Sonnet must read for context

- Constraints (file paths, test patterns)

- Acceptance criteria for verification

- Explicit instruction to run tests at the end

## Discipline rules

- One day = one focused deliverable. If it doesn't fit a day, split across days.

- Tests pass before "done." No exceptions.

- Each day stands alone. Sonnet has no memory between sessions; the prompt must be self-contained.

- Friday afternoon = review + plan next week. Don't push features to weekends.

## When a day spills over

Some days will. Realistic. Mark the day as "carried" and move the next day's task. Don't compress to maintain the schedule — quality matters more than pace.

# Phase Summary

| Phase | Days | Weeks | Calendar weeks (approx) | Pricing milestone |
| --- | --- | --- | --- | --- |
| 1: V1 Launch Ready | 1-20 | 1-4 | Weeks 1-4 | ₹999 / ₹2,999 / ₹6,999 |
| 2: Bank Reconciliation | 21-50 | 5-10 | Weeks 5-10 | ₹1,499 / ₹3,999 / ₹7,999 |
| 3: GSTN Auto-Reconciliation | 51-90 | 11-18 | Weeks 11-18 | ₹1,999 / ₹4,999 / ₹9,999 |
| 4: Tally Live Sync | 91-130 | 19-26 | Weeks 19-26 | ₹2,499 / ₹5,999 / ₹11,999 |

# Phase 1 — V1 Launch Ready (Days 1-20)

Goal: Ship a product that can be handed to a paying customer.

## Week 1: Foundation

### Day 1 — Complete demo data loader UI

Objective: Verify "Load demo data" button works end-to-end, polish error handling.

Files:

- apps/web/src/components/value-summary-banner.tsx (already partially built)

- apps/web/src/app/api/v1/onboarding/load-demo/route.ts (already built)

- apps/web/src/lib/demo-loader.ts (already built)

Implementation notes:

- Demo loader already exists from previous session

- Verify it loads 3 sample companies (kumar_textiles, sharma_electronics, techvista)

- Add loading toast + success notification using existing UI patterns

- Add unloadDemo button on dashboard once demo is loaded

Tests:

- Manual: click button, see 3 connections appear within 30 seconds

- Add API integration test: POST /api/v1/onboarding/load-demo returns 200 with 3 connections

Acceptance criteria:

- Click "Try with sample data" → 3 demo connections created

- Page refreshes to show connections list populated

- Toast notification confirms success

- If clicked twice, doesn't duplicate (idempotent)

- All existing tests still pass

Sonnet prompt:

Read these files first:
- apps/web/src/components/value-summary-banner.tsx
- apps/web/src/app/api/v1/onboarding/load-demo/route.ts
- apps/web/src/lib/demo-loader.ts

Verify the demo loader works end-to-end:
1. Confirm the button in value-summary-banner triggers POST to /api/v1/onboarding/load-demo
2. Add a success toast notification after successful load
3. Add an "Unload demo data" button that appears once demo connections exist
4. Wire it to a new endpoint /api/v1/onboarding/unload-demo (function already exists in demo-loader.ts)
5. Add an integration test for both load and unload endpoints in apps/web/src/__tests__/
6. Run `pnpm --filter web test` and ensure all pass

### Day 2 — Onboarding wizard: Step 1 (Welcome)

Objective: First screen a new user sees after signup. Two-option choice: load demo or upload your own.

Files:

- apps/web/src/app/(dashboard)/onboarding/page.tsx (new)

- apps/web/src/components/onboarding/welcome-step.tsx (new)

- apps/web/src/app/(dashboard)/page.tsx (redirect if onboarding not complete)

- packages/db/prisma/schema.prisma (User model already has onboardingComplete)

Implementation notes:

- New route /onboarding that's the landing place after first signup

- Two big buttons: "Try with demo data" (uses loader from Day 1) and "Upload my own data"

- Sets onboardingComplete=true when either path completes

- Existing dashboard redirects to /onboarding if !user.onboardingComplete

Tests:

- Component test for welcome-step rendering

- E2E flow: new user → /onboarding → click demo → /dashboard with data

Acceptance criteria:

- New signup automatically routed to /onboarding

- Two clear options shown

- Choosing demo loads sample data and goes to dashboard

- Choosing upload goes to /connections/new

Sonnet prompt:

Read:
- apps/web/src/app/(dashboard)/page.tsx
- apps/web/src/lib/auth.ts
- packages/db/prisma/schema.prisma (look at User model, note onboardingComplete field)

Build onboarding wizard step 1:
1. Create apps/web/src/app/(dashboard)/onboarding/page.tsx — protected page for first-time users
2. Create apps/web/src/components/onboarding/welcome-step.tsx with two CTAs:
   - "Try with sample data" → calls /api/v1/onboarding/load-demo → redirects to /
   - "Upload my data" → router.push('/connections/new')
3. Update apps/web/src/app/(dashboard)/page.tsx: if !user.onboardingComplete, redirect to /onboarding
4. Create POST /api/v1/onboarding/complete endpoint that sets onboardingComplete=true
5. Call /api/v1/onboarding/complete after either CTA succeeds
6. Add a Skip link for users who want to explore without onboarding
7. Use the existing UI patterns (Button, Card components)
8. Run all tests

### Day 3 — Delete connection from UI

Objective: User can remove a connection (and its data) from settings.

Files:

- apps/web/src/app/(dashboard)/connections/[id]/page.tsx (modify)

- apps/web/src/app/api/internal/connections/[id]/route.ts (already has DELETE)

- New: apps/web/src/components/connections/delete-connection-dialog.tsx

Implementation notes:

- DELETE endpoint already exists — just need UI

- Use confirmation dialog (require typing the connection name)

- On success: drop the upload table, delete UploadedFile + ErpConnection cascade

- Redirect to /connections after deletion

Tests:

- Test that DELETE cascades properly

- Test that the upload table is dropped

- Test confirmation dialog requires correct typing

Acceptance criteria:

- "Delete connection" button visible on connection page (with red accent)

- Confirmation dialog requires typing connection name

- On confirm: upload table dropped, all data removed

- User redirected to /connections with toast

Sonnet prompt:

Read:
- apps/web/src/app/(dashboard)/connections/[id]/page.tsx
- apps/web/src/app/api/internal/connections/[id]/route.ts
- packages/erp-connectors/src/file-upload/table-creator.ts (dropTempTable function)

Build the "Delete connection" UI:
1. Add a "Danger Zone" section at the bottom of /connections/[id] page
2. Create apps/web/src/components/connections/delete-connection-dialog.tsx using shadcn/ui Dialog
3. Dialog must:
   - Require typing the exact connection display name
   - Show warning text about permanent data loss
   - Disable the confirm button until name matches
4. On confirm: call DELETE /api/internal/connections/[id]
5. Make sure the existing DELETE endpoint also drops the upload_ table via dropTempTable
6. Redirect to /connections with a success toast after deletion
7. Add a test in apps/web/src/__tests__/connection-delete.test.ts
8. Run pnpm test

### Day 4 — Privacy Policy + Terms of Service pages

Objective: Legal pages required for DPDP Act compliance.

Files:

- apps/web/src/app/privacy/page.tsx (new)

- apps/web/src/app/terms/page.tsx (new)

- apps/web/src/app/layout.tsx (footer with links)

Implementation notes:

- Use the template content provided in this prompt below

- Make pages SSR-renderable (no auth required)

- Add footer to main layout with these links

- Don't claim certifications you don't have

Tests:

- Pages render at /privacy and /terms without auth

- Footer links work from any page

Acceptance criteria:

- /privacy renders standalone (no login)

- /terms renders standalone (no login)

- Both linked from app footer

- Content covers: data collection, storage, sharing, deletion, contact

Sonnet prompt:

Read:
- apps/web/src/app/layout.tsx
- packages/db/prisma/schema.prisma (to understand what data is collected)

Build Privacy Policy and Terms of Service:
1. Create apps/web/src/app/privacy/page.tsx — comprehensive DPDP-compliant privacy policy:
   - What data we collect (signup info, uploaded GL data, query history)
   - How it's stored (AWS RDS Mumbai, encryption at rest)
   - PII handling (tokenisation before LLM calls)
   - Data retention (customer-controlled)
   - User rights (export, delete, audit)
   - Contact: privacy@aiql.com
2. Create apps/web/src/app/terms/page.tsx — standard SaaS ToS:
   - Service description, account responsibilities
   - Pricing terms, refund policy (none for partial months)
   - Acceptable use, prohibited uses
   - Liability limitations (capped to fees paid)
   - Termination, governing law (Indian jurisdiction)
3. Update apps/web/src/app/layout.tsx to add a footer with: Privacy | Terms | Security | Contact
4. Run pnpm typecheck

### Day 5 — Pricing page

Objective: Public pricing page at /pricing. Three tiers + pilot program callout.

Files:

- apps/web/src/app/pricing/page.tsx (new)

- apps/web/src/components/pricing/pricing-cards.tsx (new)

- apps/web/src/lib/plans.ts (centralised plan definitions)

Implementation notes:

- Three tiers: Starter ₹999, Professional ₹2,999, Business ₹6,999

- Annual toggle (2 months free)

- Pilot callout: "First 50 customers: 50% off for 3 months"

- CTAs: "Start free trial" → /signup, "Talk to sales" → mailto

Tests:

- Pricing page renders SSR

- Toggle annual/monthly updates prices

Acceptance criteria:

- /pricing renders without auth

- 3 tier cards with features clearly listed

- Annual/monthly toggle works

- Pilot program banner prominent

- Footer FAQ section with 5-7 common questions

Sonnet prompt:

Read:
- apps/web/src/app/layout.tsx
- apps/web/src/components/ui/* (available UI primitives)

Build /pricing page:
1. Create apps/web/src/lib/plans.ts:
   - Export PLANS = [{ id, name, monthlyPrice, annualPrice, features, recommended }]
   - 3 plans: Starter ₹999, Professional ₹2,999, Business ₹6,999
   - Annual prices = monthly × 10 (2 months free)
2. Create apps/web/src/components/pricing/pricing-cards.tsx — 3-column grid with feature lists
3. Create apps/web/src/app/pricing/page.tsx with:
   - Hero: "Simple pricing. No surprises."
   - Toggle: Monthly | Annual (save 17%)
   - 3 pricing cards
   - Pilot banner: "First 50 customers get 50% off for 3 months"
   - FAQ section (collapsible)
   - Final CTA: "Start your free trial" → /signup
4. Add link to /pricing in main nav and footer
5. Run pnpm typecheck and pnpm --filter web test

## Week 2: Trust & Export

### Day 6 — PDF export for findings

Objective: "Export findings as PDF" button on close period / connection scan page.

Files:

- New: apps/web/src/lib/pdf-export.ts

- New: apps/web/src/app/api/v1/exports/findings-pdf/route.ts

- Modify: scan results UI to add button

Implementation notes:

- Use @react-pdf/renderer or generate HTML → use server-side puppeteer / playwright

- Cleanest: use pdfkit for programmatic PDF generation

- PDF includes: company name, scan date, summary stats, table of findings with severity colour coding

Tests:

- Unit test for PDF generation function (returns Buffer)

- Integration test for the export endpoint

Acceptance criteria:

- "Export PDF" button on scan results page

- Generated PDF includes all findings with ₹ amounts

- PDF has company name, period, generated-at timestamp

- Downloads as aiql-findings-{company}-{date}.pdf

Sonnet prompt:

Read:
- apps/web/src/app/(dashboard)/connections/[id]/scan/page.tsx
- packages/close-engine/src/scanner.ts (for ScanResult type)

Build PDF export for findings:
1. Install: pnpm add pdfkit @types/pdfkit --filter web
2. Create apps/web/src/lib/pdf-export.ts:
   - Function generateFindingsPdf(scanResult, connection): Promise<Buffer>
   - Header: AIQL logo (text for now), company name, scan period
   - Summary stats: total findings, total ₹ exposure, severity counts
   - Findings table grouped by severity (critical/review/info)
   - Each finding: title, affected rows, ₹ exposure, top 3 examples
   - Footer: generated-at, "AIQL ERP — aiql.io"
3. Create apps/web/src/app/api/v1/exports/findings-pdf/route.ts:
   - POST endpoint takes { connectionId, periodId? }
   - Auth check, ownership check
   - Run scan if no recent one, else use latest
   - Stream PDF response with proper Content-Type and filename headers
4. Add "Export PDF" button on the scan results page
5. Add a unit test in packages/close-engine or apps/web tests
6. Test end-to-end via curl: download a PDF for one of the validate_test connections

### Day 7 — Excel export for findings

Objective: Same data as PDF but as Excel (.xlsx) for analysis.

Files:

- New: apps/web/src/lib/excel-export.ts

- New: apps/web/src/app/api/v1/exports/findings-xlsx/route.ts

Implementation notes:

- Use exceljs library

- Multiple sheets: Summary, By Severity, All Findings (with filterable columns)

- Format ₹ amounts as currency, dates as dates

Tests:

- Unit test that returns a valid xlsx buffer

- Test that sheets contain expected data

Acceptance criteria:

- "Export Excel" button alongside PDF button

- xlsx opens cleanly in Excel and Google Sheets

- Columns are properly formatted (₹ as currency, dates as dates)

- Filterable header row enabled

Sonnet prompt:

Read:
- apps/web/src/lib/pdf-export.ts (from Day 6)
- apps/web/src/app/api/v1/exports/findings-pdf/route.ts

Build Excel export:
1. Install: pnpm add exceljs --filter web
2. Create apps/web/src/lib/excel-export.ts:
   - Function generateFindingsXlsx(scanResult, connection): Promise<Buffer>
   - Sheet 1: Summary (counts by severity, total ₹)
   - Sheet 2: All Findings (columns: code, severity, title, rows, exposure, action)
   - Sheet 3: Top Issues (top 10 by exposure)
   - Use exceljs cell formats: currency for ₹, date for timestamps
   - Enable filter on header row
   - Freeze first row
3. Create apps/web/src/app/api/v1/exports/findings-xlsx/route.ts (mirror PDF endpoint)
4. Add "Export Excel" button next to "Export PDF" on scan results page
5. Unit test that opening the file returns expected sheets/cells

### Day 8 — Security one-pager at /security

Objective: Public page explaining security posture. Linked from footer.

Files:

- New: apps/web/src/app/security/page.tsx

Implementation notes:

- Cover: encryption at rest, in transit, PII tokenisation, data residency, retention, deletion rights, contact

- Don't claim certifications you don't have (no SOC 2, no ISO yet)

- Honest current state with roadmap items marked "in progress"

Tests:

- Page renders SSR without auth

- Linked from footer

Acceptance criteria:

- /security renders cleanly

- All 8 sections present

- No false claims (no SOC 2 yet, no ISO yet)

- Contact: security@aiql.com

Sonnet prompt:

Build /security page with these sections:

1. Data residency — AWS RDS ap-south-1 (Mumbai)
2. Encryption at rest — AES-256 via AWS KMS
3. Encryption in transit — TLS 1.3
4. PII handling — tokenised before LLM calls, never logged in plaintext, never sent to third-party AI providers raw
5. Authentication — Lucia + argon2 password hashing, optional 2FA (planned Q3 2026)
6. Access controls — role-based, audit logged
7. Data retention — customer-controlled, default 365 days, deletion within 24 hours of request
8. Compliance posture — DPDP Act aligned (current), ISO 27001 (in progress Q3 2026), SOC 2 Type II (planned Q1 2027)
9. Incident response — disclosure within 24 hours per DPDP Act
10. Contact — security@aiql.com

Use clean visual hierarchy: section headers, icons (lucide-react), short paragraphs. No tables.
Add to footer alongside Privacy / Terms / Contact.

### Day 9 — Sentry error monitoring

Objective: Server + client errors logged to Sentry. You see them before customers report.

Files:

- New: apps/web/sentry.client.config.ts

- New: apps/web/sentry.server.config.ts

- New: apps/web/sentry.edge.config.ts

- Modify: apps/web/next.config.js

- Modify: .env (add SENTRY_DSN)

Implementation notes:

- Sign up for Sentry free tier at sentry.io

- Get DSN, add to .env

- Use @sentry/nextjs with default config

- Mask PII in error context (don't log party names, amounts)

Tests:

- Throw a test error, confirm it appears in Sentry dashboard

- Verify PII is masked in the error context

Acceptance criteria:

- @sentry/nextjs installed and configured

- SENTRY_DSN in .env

- Throw an error in dev, see it in Sentry dashboard

- PII (party_name, amount) is scrubbed from error context

Sonnet prompt:

The user needs to provide a Sentry DSN. Either:
(a) Ask them to sign up at sentry.io free tier and provide DSN
(b) Set up with a placeholder DSN they can swap later

Install and configure Sentry for Next.js:
1. pnpm add @sentry/nextjs --filter web
2. Run `npx @sentry/wizard@latest -i nextjs` OR manually create:
   - apps/web/sentry.client.config.ts
   - apps/web/sentry.server.config.ts
   - apps/web/sentry.edge.config.ts
3. Wrap next.config.js with withSentryConfig
4. Add scrub rules: redact party_name, vendor_name, customer_name, amount fields from error context
5. Add to .env.example: SENTRY_DSN=
6. Test by adding an intentional throw in a test API route, verify it appears in Sentry

### Day 10 — LLM cost guardrails (verify + enforce)

Objective: Confirm queryLimit is enforced. Add hard daily cap per org.

Files:

- Audit: apps/web/src/app/api/v1/query/route.ts

- Audit: apps/web/src/app/api/v1/llm-proxy/chat/route.ts

- New if needed: apps/web/src/lib/usage-guardrails.ts

Implementation notes:

- Check if queriesUsed >= queryLimit blocks queries currently

- If not, add the check at the start of every LLM-calling endpoint

- Add daily cap: 100 queries/day per org regardless of plan (prevent runaway)

- Return 429 with friendly message: "Daily limit reached, contact support"

Tests:

- Test that 101st query in a day is blocked

- Test that queryLimit blocks at plan limit

- Test that resetting queriesResetAt clears the counter

Acceptance criteria:

- Daily hard cap enforced (100/day default)

- Plan limit enforced (queryLimit from Organisation)

- Resetting monthly (queriesResetAt cron job)

- Returns 429 with clear message

Sonnet prompt:

Read:
- apps/web/src/app/api/v1/query/route.ts
- apps/web/src/app/api/v1/llm-proxy/chat/route.ts
- packages/db/prisma/schema.prisma (Organisation.queriesUsed, queryLimit, queriesResetAt)

Audit and enforce LLM cost guardrails:
1. Check if queryLimit is currently enforced in the query route. If not, add it.
2. Create apps/web/src/lib/usage-guardrails.ts:
   - checkOrgQueryAllowance(orgId): Promise<{ allowed: boolean; reason?: string; resetAt?: Date }>
   - incrementOrgQueryCount(orgId): Promise<void>
   - Both wrapped in a transaction to avoid races
3. Add a DAILY_LIMIT constant (default 100/day per org) on top of monthly queryLimit
4. Track daily via a new field (or use a Redis-like in-memory cache for first version)
5. Call checkOrgQueryAllowance() at start of /api/v1/query and /api/v1/llm-proxy/chat
6. Increment after successful response
7. Return 429 with JSON: { error, dailyLimitReached, planLimitReached, resetAt }
8. Write tests for both limits

## Week 3: Authentication & Billing

### Day 11 — Email service integration (Resend)

Objective: Centralised email sending via Resend. Templates for transactional emails.

Files:

- Modify: apps/web/src/lib/email.ts (currently stub)

- Add: apps/web/src/lib/email-templates/ (HTML templates)

- Add Resend API key to .env

Implementation notes:

- Sign up at resend.com (free tier: 100/day, 3K/month)

- Verify aiql.io domain (DNS records)

- Create base template + 3 specific: verify-email, reset-password, welcome

- Use React Email or simple HTML strings

Tests:

- Mock Resend client in tests

- Test that emails fire on signup, verification, password reset

Acceptance criteria:

- Resend account set up, domain verified

- sendEmail() function in email.ts

- 3 templates ready: verifyEmail, resetPassword, welcome

- Test email sends successfully in dev

Sonnet prompt:

The user needs to provide a Resend API key. If not provided, use a stub that logs to console.

Read:
- apps/web/src/lib/email.ts (current stub)

Build email infrastructure:
1. pnpm add resend --filter web
2. Update apps/web/src/lib/email.ts:
   - export async function sendEmail({ to, subject, html, from? }): Promise<void>
   - Use Resend client when RESEND_API_KEY is set, else console.log
3. Create apps/web/src/lib/email-templates/:
   - base.ts — wrapper layout (header, body, footer, AIQL branding)
   - verify-email.ts — verification link template
   - reset-password.ts — reset link template
   - welcome.ts — first-time user welcome
4. Each template: takes data object, returns { subject, html }
5. Add RESEND_API_KEY to .env.example
6. Add a test API route /api/internal/test-email (dev only) to send a test
7. Test by running the dev server and hitting the test endpoint

### Day 12 — Email verification on signup

Objective: New signups must verify email before they can use the app.

Files:

- Modify: apps/web/src/app/api/auth/signup/route.ts

- Modify: packages/db/prisma/schema.prisma (add User.emailVerified, User.verificationToken)

- New: apps/web/src/app/api/auth/verify-email/route.ts

- New: apps/web/src/app/verify-email/page.tsx

Implementation notes:

- Add emailVerified: DateTime? and verificationToken: String? to User

- On signup: create user with emailVerified: null, send verification email

- Verify endpoint: token → mark verified, clear token

- Login allowed but limited (banner: "Please verify your email")

- Hard-block after 7 days

Tests:

- Test signup creates user with unverified status

- Test verification endpoint marks user verified

- Test expired token rejected

Acceptance criteria:

- Signup sends verification email

- Click link → user verified

- Verification token expires after 7 days

- Unverified users see a banner

Sonnet prompt:

Read:
- apps/web/src/app/api/auth/signup/route.ts
- apps/web/src/lib/email.ts (from Day 11)
- packages/db/prisma/schema.prisma (User model)

Build email verification:
1. Update Prisma schema — add to User:
   - emailVerifiedAt: DateTime?
   - verificationToken: String?
   - verificationExpiresAt: DateTime?
2. Run prisma generate (skip db push — use ALTER TABLE via direct SQL like we did before for the lastAppliedAt field)
3. Update signup route:
   - Generate verification token (crypto.randomBytes(32).toString('hex'))
   - Set verificationExpiresAt = now + 7 days
   - Send verification email
4. Create /api/auth/verify-email?token=xxx endpoint:
   - Find user by token
   - Check not expired
   - Set emailVerifiedAt, clear token
5. Create /verify-email page that calls the endpoint
6. Add banner to dashboard if !user.emailVerifiedAt
7. Tests

### Day 13 — Password reset flow

Objective: User can reset forgotten password via email link.

Files:

- New: apps/web/src/app/(auth)/forgot-password/page.tsx

- New: apps/web/src/app/(auth)/reset-password/page.tsx

- New: apps/web/src/app/api/auth/forgot-password/route.ts

- New: apps/web/src/app/api/auth/reset-password/route.ts

- Schema: add User.resetToken, User.resetExpiresAt

Implementation notes:

- /forgot-password: enter email → triggers reset email (always returns success to prevent email enumeration)

- /reset-password?token=xxx: form to set new password

- Token expires in 1 hour

- After reset: invalidate all existing sessions

Tests:

- Test request always returns success

- Test reset with valid token works

- Test reset with expired token rejected

- Test sessions invalidated after reset

Acceptance criteria:

- "Forgot password?" link on login page

- Email sent with reset link (or success returned silently if email doesn't exist)

- Reset page accepts new password

- Token expires in 1 hour

- All sessions invalidated after reset

Sonnet prompt:

Read:
- apps/web/src/app/(auth)/login/page.tsx
- apps/web/src/app/api/auth/login/route.ts
- apps/web/src/lib/email.ts

Build password reset flow:
1. Schema additions (use direct SQL ALTER):
   - User.resetToken: String?
   - User.resetExpiresAt: DateTime?
2. Create /forgot-password page with email form
3. Create /api/auth/forgot-password:
   - Look up user by email
   - Generate token, set 1-hour expiry
   - Send reset email
   - ALWAYS return 200 (no enumeration)
4. Create /reset-password page with token (query param) + new password form
5. Create /api/auth/reset-password:
   - Validate token
   - Hash new password (argon2)
   - Update user
   - Clear token
   - Invalidate all sessions (lucia.invalidateUserSessions)
6. Add "Forgot password?" link to login page
7. Create reset-password.ts email template (already started Day 11)
8. Tests for all paths

### Day 14 — Razorpay integration (account + checkout)

Objective: Customer can upgrade plan via Razorpay checkout. Webhook updates DB.

Files:

- New: apps/web/src/lib/razorpay.ts

- New: apps/web/src/app/api/v1/billing/create-order/route.ts

- New: apps/web/src/app/api/v1/billing/webhook/route.ts

- Modify: schema add Subscription model (or just Organisation fields)

Implementation notes:

- Sign up at razorpay.com (KYC required, takes 1-2 days for business)

- Use Razorpay Subscriptions (recurring) not one-time orders

- Plans created in Razorpay dashboard, IDs stored in env

- Webhook verifies signature, updates Organisation.stripeSubscriptionId (rename to billingId)

Tests:

- Mock Razorpay client

- Test webhook signature validation

- Test subscription state updates

Acceptance criteria:

- Razorpay account set up + plans created

- /api/v1/billing/create-order creates a Razorpay subscription

- Webhook receives + verifies + updates DB

- Settings page shows current plan + "Manage billing" link

Sonnet prompt:

The user needs to set up a Razorpay account first (requires KYC). For now, set up with test API keys.

Read:
- packages/db/prisma/schema.prisma (Organisation model — note stripeCustomerId/stripeSubscriptionId fields)
- apps/web/src/lib/plans.ts (from Day 5)

Build Razorpay subscription integration:
1. pnpm add razorpay --filter web
2. Create apps/web/src/lib/razorpay.ts:
   - Razorpay client initialised with env keys
   - createSubscription(planId, customerInfo): Promise<{ subscriptionId, shortUrl }>
   - cancelSubscription(subscriptionId): Promise<void>
   - verifyWebhookSignature(body, signature, secret): boolean
3. Create /api/v1/billing/create-order:
   - Takes { planTier: 'starter' | 'professional' | 'business' }
   - Auth required, gets org
   - Creates Razorpay subscription
   - Returns checkout URL
4. Create /api/v1/billing/webhook:
   - Verify Razorpay signature
   - Handle events: subscription.activated, subscription.charged, subscription.cancelled
   - Update Organisation.stripeSubscriptionId (or rename to billingSubscriptionId)
   - Update plan field accordingly
5. Add RAZORPAY_KEY_ID, RAZORPAY_KEY_SECRET, RAZORPAY_WEBHOOK_SECRET to .env.example
6. Tests for webhook signature verification

### Day 15 — Plan upgrade/downgrade UI

Objective: User can change plans from /settings/billing.

Files:

- New or modify: apps/web/src/app/(dashboard)/settings/billing/page.tsx

- New: apps/web/src/components/billing/plan-card.tsx

- New: apps/web/src/app/api/v1/billing/change-plan/route.ts

Implementation notes:

- Show current plan with usage metrics

- Show other plans with "Upgrade" / "Downgrade" buttons

- On change: cancel current Razorpay subscription, create new one

- Show pro-rated bill explanation

Tests:

- Test plan change cancels old, creates new

- Test downgrade preserves grandfather pricing

Acceptance criteria:

- /settings/billing shows current plan + usage

- Other plans displayed with clear upgrade/downgrade paths

- Click button → Razorpay checkout → webhook updates DB → success

- Confirmation dialog for downgrades

Sonnet prompt:

Read:
- apps/web/src/lib/plans.ts (from Day 5)
- apps/web/src/lib/razorpay.ts (from Day 14)
- apps/web/src/app/(dashboard)/settings/ (existing settings layout)

Build /settings/billing page:
1. If billing page exists, audit it. Else create.
2. Create apps/web/src/components/billing/plan-card.tsx — single plan display with action button
3. Page sections:
   - Current plan summary (name, price, billing date, usage: queries used/limit)
   - All available plans (3 cards) with Upgrade/Downgrade CTAs
   - Cancel subscription button (with confirmation)
4. Create /api/v1/billing/change-plan:
   - Cancel current subscription
   - Create new at the new plan
   - Update DB
5. Show pro-rated bill explanation
6. Add tests

## Week 4: Differentiator + Polish

### Day 16 — TDS deduction scanner check (Section 40(a)(ia))

Objective: Add a scanner check that flags vendor payments above ₹30K with no TDS deducted.

Files:

- Modify: packages/close-engine/src/scanner.ts (add check function)

- Tests: packages/close-engine/src/__tests__/scanner.test.ts

Implementation notes:

- TDS thresholds for 194C (contractor): single payment ₹30K OR aggregate ₹1L/year

- Detection: find vendor payments where party_name exists, voucher_type = Payment, amount > threshold, and no corresponding TDS entry on the same voucher

- Output: list of vouchers + total ₹ exposure (which = the disallowed expense risk)

Tests:

- Mock SQL returns vendor payments > 30K

- Verify check identifies them as missing TDS

Acceptance criteria:

- New check function checkTdsDeduction added

- Returns Issue with code tds_missing

- Wired into runDataQualityScan parallel execution

- Test cases cover: single payment > 30K, aggregate > 1L, payment with TDS (should NOT flag)

Sonnet prompt:

Read:
- packages/close-engine/src/scanner.ts
- packages/close-engine/src/__tests__/scanner.test.ts (existing pattern for tests with mocked prisma)

Add TDS deduction scanner check (Section 40(a)(ia)):

1. Add function checkTdsDeduction(table, start, end, colMap, presentColumns) in scanner.ts:
   - SQL: find payment vouchers where party_name IS NOT NULL, sum(debit_amount) > 30000 per voucher
   - Cross-check: no entry with account_name LIKE '%TDS%' in same voucher (reference_number match)
   - Return Issue: code='tds_missing', severity='critical'
   - title: "N vendor payments missing TDS deduction"
   - exposure = sum of payments (this is the disallowed expense risk)
2. Add to runDataQualityScan parallel checks array
3. Add issue title mapping in task-generator.ts:
   tds_missing: "Add TDS deduction for ${N} vendor payments"
4. Add tests in scanner.test.ts:
   - Mock returns 3 payments, each above 30K, no TDS
   - Assert issue.affectedRows = 3
   - Assert issue.severity = 'critical'
5. Run pnpm test

### Day 17 — Cash payment > ₹10K scanner check (Section 40A(3))

Objective: Flag cash payments above ₹10K — Income Tax Act disallows the expense.

Files:

- Modify: packages/close-engine/src/scanner.ts

- Tests: same file

Implementation notes:

- Detection: voucher_type = Payment, account_name LIKE '%cash%' (or Petty Cash etc.), debit_amount > 10000

- Section 40A(3) disallows cash payments > ₹10,000 single transaction (₹35K for transporters)

Tests:

- Mock cash payment > 10K → flag

- Mock cash payment <= 10K → don't flag

Acceptance criteria:

- Function checkCashPayments added

- Returns Issue with code cash_payment_excess

- Threshold configurable (default 10000)

- Tests pass

Sonnet prompt:

Read: packages/close-engine/src/scanner.ts (and the TDS check from Day 16 as reference)

Add Cash payment > ₹10K check (Section 40A(3)):
1. Function checkCashPayments(...): looks for cash account payments above ₹10,000
2. SQL: LOWER(account_name) LIKE '%cash%' OR LIKE '%petty cash%', voucher_type='Payment', sum(debit_amount) per voucher > 10000
3. Issue: code='cash_payment_excess', severity='review', exposure = sum (disallowance risk)
4. Title: "${N} cash payments above ₹10K — Section 40A(3) disallowance risk"
5. Add to runDataQualityScan parallel checks
6. Add tests

### Day 18 — Cash receipt > ₹2L scanner check (Section 269ST)

Objective: Flag cash receipts above ₹2 lakh — penalty under Section 269ST.

Files:

- Modify: packages/close-engine/src/scanner.ts

- Tests: same file

Implementation notes:

- Detection: voucher_type = Receipt, account_name LIKE '%cash%', credit_amount > 200000

- Section 269ST: penalty = amount received in cash above ₹2L

Tests:

- Mock cash receipt > 2L → flag with severity critical (penalty equal to amount)

Acceptance criteria:

- Function checkCashReceipts added

- Returns Issue with code cash_receipt_excess

- Severity: critical (penalty equal to amount)

- Tests pass

Sonnet prompt:

Read: packages/close-engine/src/scanner.ts (and existing checks as reference)

Add Cash receipt > ₹2L check (Section 269ST):
1. Function checkCashReceipts: looks for cash account receipts above ₹2,00,000 single transaction
2. SQL: similar to cash payment but Receipt type and credit_amount instead
3. Issue: code='cash_receipt_excess', severity='critical', exposure = sum (penalty equals amount)
4. Title: "${N} cash receipts above ₹2L — Section 269ST penalty risk"
5. Add to runDataQualityScan
6. Tests

### Day 19 — Account deletion / data export (DPDP compliance)

Objective: User can delete their account and export all their data.

Files:

- New: apps/web/src/app/(dashboard)/settings/data/page.tsx

- New: apps/web/src/app/api/v1/account/export/route.ts

- New: apps/web/src/app/api/v1/account/delete/route.ts

Implementation notes:

- Export: ZIP with org info, connections, scans, queries, knowledge entries — JSON files

- Delete: confirmation dialog (type org name), cascade delete (Cascade in schema handles most), drop upload tables

Tests:

- Test export generates valid ZIP

- Test delete removes all data

Acceptance criteria:

- /settings/data shows data overview + Export + Delete buttons

- Export downloads ZIP with all org data

- Delete requires typing org name + sends confirmation email + 24h grace period

Sonnet prompt:

Read:
- apps/web/src/app/(dashboard)/settings/ (existing pages)
- packages/db/prisma/schema.prisma (all org-related models)

Build DPDP-compliant account management:
1. Create /settings/data page with:
   - Data overview (X connections, Y MB stored, Z queries logged)
   - "Export all data" button
   - "Delete account" button (danger zone)
2. Create /api/v1/account/export:
   - Gather: org info, all connections, all uploads, all scans, all queries, all knowledge
   - Anonymise tokens if needed
   - Generate ZIP using node:archiver
   - Stream response with proper headers
3. Create /api/v1/account/delete:
   - Require org name typed exactly
   - Send email to all team members
   - Schedule deletion 24 hours later (immediate for now — add scheduling later)
   - Drop all upload_ tables
   - Delete Organisation (cascades to all related)
4. Tests

### Day 20 — Audit log for PII access

Objective: Log who in the org accessed which connection's data, when. Surface in settings.

Files:

- Schema: add ConnectionAccessLog model

- New: apps/web/src/lib/audit-log.ts

- Modify: connection-viewing pages to log

- New: apps/web/src/app/(dashboard)/settings/audit/page.tsx

Implementation notes:

- New table: connection access log (userId, connectionId, action, timestamp, ipAddress)

- Log on every page view of /connections/[id], scan, query

- Settings page lists last 100 entries with filters

Tests:

- Test that visiting a connection page creates a log entry

- Test that settings page renders logs

Acceptance criteria:

- Schema updated with ConnectionAccessLog

- Logging middleware/helper in place

- /settings/audit page shows recent access

- Filters: by user, by connection, by action

Sonnet prompt:

Read: packages/db/prisma/schema.prisma

Build PII access audit logging:
1. Schema (use ALTER TABLE direct SQL, not prisma db push):
   ConnectionAccessLog {
     id           String   @id @default(cuid())
     orgId        String
     userId       String
     connectionId String?
     action       String   // 'view', 'scan', 'query', 'export'
     ipAddress    String?
     userAgent    String?
     metadata     String?  // JSON for action-specific data
     createdAt    DateTime @default(now())
     @@index([orgId, createdAt])
   }
2. Create apps/web/src/lib/audit-log.ts:
   - logAccess({ userId, orgId, connectionId, action, request }): Promise<void>
   - Best-effort (don't fail the parent request)
3. Add log calls in:
   - /connections/[id] page (action: 'view')
   - /api/v1/connections/[connectionId]/scan (action: 'scan')
   - /api/v1/query (action: 'query')
   - export endpoints (action: 'export')
4. Create /settings/audit page:
   - Table of last 100 entries
   - Filters: user, connection, action, date range
   - CSV export of full log
5. Tests

# Phase 2 — Bank Reconciliation (Days 21-50)

Goal: Add the most-used CA workflow. Converts AIQL from monthly scanner to weekly tool.

## Weeks 5-6: PDF Parsers

### Day 21 — Bank statement schema design

Objective: Database tables for bank statements, transactions, match status.

Files:

- Schema: add BankStatement, BankTransaction, BankMatch

- Migration via direct SQL

Implementation notes:

- BankStatement: per-upload metadata (bank, account, period, file)

- BankTransaction: individual rows from statement (date, amount, type, description)

- BankMatch: links bank transaction to GL voucher (or 'unmatched')

Tests:

- Schema validates

- Basic CRUD works

Acceptance criteria:

- 3 new tables in schema

- Migrations applied

- Prisma client regenerated

Sonnet prompt:

Read: packages/db/prisma/schema.prisma

Design bank reconciliation schema. Add 3 models:

BankStatement {
  id              String @id @default(cuid())
  connectionId    String
  bankName        String     // 'HDFC', 'ICICI', 'SBI', 'Axis', 'OTHER'
  accountNumber   String     // last 4 digits stored, full encrypted
  periodStart     DateTime
  periodEnd       DateTime
  openingBalance  Decimal
  closingBalance  Decimal
  originalFile    String?    // S3 key
  uploadedAt      DateTime @default(now())
  transactions    BankTransaction[]
}

BankTransaction {
  id              String @id @default(cuid())
  statementId     String
  transactionDate DateTime
  description     String
  referenceNumber String?    // cheque no, UTR, etc.
  amount          Decimal    // positive = credit, negative = debit
  balance         Decimal?
  matchedTo       BankMatch?
  @@index([statementId])
}

BankMatch {
  id                  String @id @default(cuid())
  bankTransactionId   String @unique
  voucherReference    String?  // GL reference_number
  matchConfidence     Float    // 0-1
  matchType           String   // 'exact', 'fuzzy', 'manual', 'unmatched'
  inTransit           Boolean @default(false)
  note                String?
  matchedBy           String?
  matchedAt           DateTime?
}

Apply via ALTER TABLE direct SQL (similar to the OrgBusinessKnowledge migration pattern).
Run prisma generate.

### Day 22-24 — HDFC PDF parser

Day 22 Objective: Extract transactions from a standard HDFC bank statement PDF.

Day 23 Objective: Handle HDFC PDF format variations.

Day 24 Objective: Tests + edge cases (multi-page, transactions split across pages).

Files:

- New: packages/bank-recon/src/parsers/hdfc.ts

- New: packages/bank-recon/src/parsers/types.ts

- Tests: packages/bank-recon/src/__tests__/hdfc.test.ts

Implementation notes:

- New monorepo package: packages/bank-recon

- Use pdf-parse to extract text, then regex/parsing rules

- HDFC has predictable format: Date | Narration | Chq/Ref | Value Date | Withdrawal | Deposit | Balance

- Need 5+ real HDFC statements to test against

Tests:

- Parse a known HDFC statement, assert specific transactions extracted

- Edge cases: multi-line narration, empty cells, footer pages

Acceptance criteria:

- Function parseHdfcStatement(buffer): Promise<BankStatement> returns structured data

- Handles 3+ format variations

- Tests with 5+ real (sanitised) HDFC PDFs

Sonnet prompt (Day 22):

Create new monorepo package packages/bank-recon. Mimic the structure of packages/close-engine.

Build HDFC bank statement PDF parser:
1. pnpm add pdf-parse --filter @aiql/bank-recon
2. Create packages/bank-recon/src/parsers/types.ts:
   - ParsedStatement type matching the BankStatement schema
   - ParsedTransaction type matching BankTransaction schema
3. Create packages/bank-recon/src/parsers/hdfc.ts:
   - export async function parseHdfcStatement(buffer: Buffer): Promise<ParsedStatement>
   - Use pdf-parse to extract text
   - Detect HDFC format: header contains "HDFC BANK", account number in standard place
   - Extract: account number, period, opening/closing balance
   - Parse transaction rows: Date | Narration | Chq No | Value Date | Withdrawal | Deposit | Balance
   - Convert to ParsedTransaction[]
4. Create packages/bank-recon/package.json with proper dependencies
5. Write tests/__tests__/hdfc.test.ts with a sample HDFC text dump (no real PDF in repo)
6. The user will provide a real HDFC PDF for manual verification

Day 23-24 follow on the same pattern — refine the parser, add format variations, comprehensive tests.

### Day 25-26 — ICICI PDF parser

Same pattern as HDFC. ICICI format is similar but column order differs.

Sonnet prompt (Day 25):

Read:
- packages/bank-recon/src/parsers/hdfc.ts (built Day 22-24)
- packages/bank-recon/src/parsers/types.ts

Build ICICI bank statement parser following the HDFC pattern:
1. Create packages/bank-recon/src/parsers/icici.ts
2. ICICI format: Date | Mode | Particulars | Deposits | Withdrawals | Balance
3. Header marker: "ICICI BANK" + account number format
4. Same return type ParsedStatement
5. Tests in packages/bank-recon/src/__tests__/icici.test.ts

### Day 27-28 — SBI PDF parser

Same pattern. SBI has the most format variations of major Indian banks.

### Day 29 — Axis Bank PDF parser

Same pattern.

### Day 30 — Generic CSV import + parser dispatcher

Objective: Fallback CSV parser + auto-detect which parser to use based on PDF header.

Files:

- New: packages/bank-recon/src/parsers/csv.ts

- New: packages/bank-recon/src/parsers/dispatcher.ts

Sonnet prompt:

Read all parsers in packages/bank-recon/src/parsers/ (HDFC, ICICI, SBI, Axis)

Build:
1. Generic CSV parser:
   - Auto-detect columns using @aiql/erp-connectors mapColumn function
   - Map to ParsedTransaction[]
2. Parser dispatcher:
   - Function detectBankStatement(buffer, filename): { parser: 'hdfc' | 'icici' | 'sbi' | 'axis' | 'generic_csv', confidence: number }
   - Read first page of PDF / first 5 lines of CSV
   - Look for bank-specific markers
   - Return appropriate parser
3. Main entry: parseBankStatement(buffer, filename, hint?): ParsedStatement
   - Use dispatcher, then call appropriate parser
   - Fall back to CSV if PDF doesn't match known formats
4. Tests for dispatcher with each bank format

## Weeks 7-8: Matching Engine

### Day 31 — Bank statement upload UI + API

Objective: User uploads a bank statement; AIQL parses, stores, shows summary.

Files:

- New: apps/web/src/app/(dashboard)/connections/[id]/bank-recon/page.tsx

- New: apps/web/src/app/(dashboard)/connections/[id]/bank-recon/upload/page.tsx

- New: apps/web/src/app/api/v1/bank-recon/upload/route.ts

Implementation notes:

- Upload page with drag-drop file

- POST file to /api/v1/bank-recon/upload

- Parse, store BankStatement + BankTransactions

- Redirect to /bank-recon/{statementId}

Sonnet prompt:

Read:
- apps/web/src/app/(dashboard)/connections/[id]/page.tsx
- packages/bank-recon/* (parsers built Days 22-30)

Build bank statement upload:
1. /api/v1/bank-recon/upload POST endpoint:
   - Accept multipart file
   - Determine connectionId from query/body
   - Use bank-recon dispatcher to detect format
   - Parse statement
   - Store BankStatement + BankTransactions in DB
   - Return statementId
2. /connections/[id]/bank-recon/upload page:
   - Drag-drop file input
   - Bank format selector (or auto-detect)
   - Submit → call API → redirect to results
3. /connections/[id]/bank-recon page:
   - List uploaded statements for this connection
   - "Upload new" CTA
4. Tests for upload endpoint

### Day 32 — Exact matching algorithm

Objective: Match bank transactions to GL vouchers where amount + date + ref number match exactly.

Files:

- New: packages/bank-recon/src/matching/exact.ts

- New: apps/web/src/app/api/v1/bank-recon/[statementId]/match/route.ts

Implementation notes:

- Query all GL vouchers in the bank statement's period

- For each bank transaction, look for: voucher with same amount, same date (or ±1 day), same ref if available

- High-confidence exact matches (1.0)

- Store as BankMatch with type='exact'

Sonnet prompt:

Build exact matching engine:
1. Create packages/bank-recon/src/matching/exact.ts:
   - Function exactMatch(bankTransaction, glVouchers): MatchResult | null
   - Match criteria: same amount (±₹0.50), same date (±1 day), same reference if available
   - Returns { voucherReference, confidence: 1.0 } or null
2. Create /api/v1/bank-recon/[statementId]/match POST endpoint:
   - Load all bank transactions for statement
   - Query GL vouchers in statement's period
   - For each bank transaction, attempt exact match
   - Store BankMatch records
   - Return summary
3. Tests with mocked GL data

### Day 33 — Fuzzy matching algorithm

Objective: Match remaining (unmatched-after-exact) transactions using fuzzy criteria.

Files:

- New: packages/bank-recon/src/matching/fuzzy.ts

Implementation notes:

- For unmatched bank transactions, look for:

  - Same amount (±₹1), date within ±7 days, description contains vendor name

  - Or description similar to voucher narration (Levenshtein distance)

- Confidence based on closeness: 0.7-0.95

- Store with type='fuzzy'

Sonnet prompt:

Build fuzzy matching:
1. packages/bank-recon/src/matching/fuzzy.ts:
   - fuzzyMatch(bankTransaction, glVouchers): MatchResult | null
   - Scoring: amount weight 50%, date weight 30%, description similarity 20%
   - Threshold: confidence >= 0.7 to suggest a match
2. Integrate into match endpoint from Day 32 (run fuzzy after exact for remaining)
3. Tests

### Day 34 — Match scoring + confidence levels

Objective: Combine exact + fuzzy results, surface confidence for user review.

Sonnet prompt:

Refine matching engine:
1. Combine exact + fuzzy results
2. Add confidence buckets:
   - 'high' (0.95-1.0): auto-confirm, show as matched
   - 'medium' (0.7-0.94): show as "review suggested"
   - 'low' (<0.7): show as unmatched
3. Update BankMatch records with confidence bucket
4. Tests

### Day 35 — Match results storage + retrieval

Sonnet prompt:

Build match results API:
1. GET /api/v1/bank-recon/[statementId]/matches:
   - Returns categorized: matched (exact), suggested (fuzzy), unmatched (bank side), unmatched (book side)
   - Pagination for large statements
2. GET /api/v1/bank-recon/[statementId] returns statement summary + match counts
3. Tests

### Day 36-37 — Manual match UI + persistence

Sonnet prompt (Day 36):

Build manual match UI:
1. /connections/[id]/bank-recon/[statementId] page:
   - Three columns: Matched | Suggested | Unmatched
   - Each transaction shows date, description, amount
   - Suggested matches show confidence and proposed voucher
   - Click "Confirm" / "Reject" / "Match to..."
2. "Match to..." opens modal with searchable list of unmatched GL vouchers
3. Drag-drop variant (post-MVP)
4. Tests

### Day 38-39 — In-transit tracking + carry-forward

Sonnet prompt (Day 38):

Add in-transit tracking:
1. UI option to mark unmatched transaction as "in transit" (cheque issued but not cleared)
2. Updates BankMatch.inTransit = true
3. Next month: these transactions appear in "carried forward" section
4. Tests

### Day 40 — Tests for matching engine

Sonnet prompt:

Add comprehensive integration tests for bank-recon:
- End-to-end: upload statement → match → store → retrieve
- Edge cases: zero transactions, all match, none match
- Performance: 10K transactions match in < 30 seconds

## Weeks 9-10: Workflow Integration

### Day 41-42 — Bank Recon dashboard + discrepancy report PDF

Day 41:

Build Bank Recon dashboard:
- Summary cards: matched count, unmatched bank, unmatched book, variance ₹
- Three-bucket detail view (clickable)
- "Export discrepancy report" button

Day 42:

Reuse pdf-export pattern from Day 6:
- Generate discrepancy report PDF
- Include all unmatched transactions
- Recommended actions

### Day 43-44 — Recurring patterns detection

Detect recurring patterns:
- "Bank charges always match — auto-confirm next time"
- "Same vendor pays monthly with similar reference — high confidence match"
- Reduce review time on subsequent statements

### Day 45 — Bank Recon as close period task

Integrate into Close Manager:
- Generate "Reconcile bank account" task during close period creation if BANK accounts exist
- Task links to bank-recon page
- Mark complete when all transactions matched or marked

### Days 46-50 — Multi-bank support, polish, tests, launch

Day 46: Multi-bank per entity support Day 47: End-to-end tests Day 48: UI polish Day 49: Documentation Day 50: Phase 2 launch + pricing announcement email

# Phase 3 — GSTN Auto-Reconciliation (Days 51-90)

Goal: Auto-pull GSTR-2A/2B from GST portal, reconcile against books. Major pricing justifier.

Prerequisites:

- GSTN sandbox API access (apply Week 1 of Phase 1 — 6-week approval)

- GSP partnership decided (or direct integration)

## Weeks 11-12: GSTN API Integration

### Days 51-55 — GSTN authentication

Day 51: GSTN sandbox status, document API contract, set up env vars Day 52: Authentication flow — GSTIN registration Day 53: OTP flow handling (UI + API) Day 54: Session management + auth token storage Day 55: Token refresh logic

Sonnet prompt (Day 52):

GSTN API requires GSP (GST Suvidha Provider) credentials. The user must have these set up.

Read GSTN public API documentation: https://docs.gstn.org/

Build GSTN authentication module:
1. Create packages/gstn-integration/ monorepo package
2. Authentication flow:
   - User enters GSTIN
   - Backend calls GSTN auth API
   - GSTN sends OTP to registered mobile/email
   - User enters OTP
   - Backend exchanges for access token
3. Store encrypted tokens per organisation (use existing crypto infra)
4. Token TTL handling (refresh before expiry)
5. Tests with mocked GSTN responses

### Days 56-60 — Rate limiting, error handling, testing, encryption, UI

Day 56: Rate limiting (GSTN throttles aggressively) + retry logic with backoff Day 57: Comprehensive error handling for GSTN-specific errors Day 58: Sandbox testing scenarios (success, OTP fail, throttle, expired token) Day 59: GSTN connection UI (Settings → Integrations → GSTN) Day 60: Encrypted credential storage

## Weeks 13-14: GSTR-2A/2B Pull

### Days 61-65 — GSTR-2A + 2B pull and parse

Day 61: GSTR-2A pull endpoint Day 62: GSTR-2A JSON parsing Day 63: GSTR-2A storage schema (GstrPullRecord, GstrInvoice) Day 64: GSTR-2B pull endpoint Day 65: GSTR-2B JSON parsing

### Days 66-70 — Schema, scheduler, aggregation, status tracking, tests

Day 66: GSTR-2B storage + invoice-level records Day 67: Monthly pull scheduler (cron or queue-based) Day 68: Vendor-wise aggregation queries Day 69: Supplier filing status tracking Day 70: Tests for full pull pipeline

## Weeks 15-16: Reconciliation Engine

### Days 71-75 — Comparison logic

Day 71: Books ITC vs 2B ITC comparison engine Day 72: Invoice-level matching algorithm (invoice no + amount + date + GSTIN) Day 73: Match scoring for invoices Day 74: Rule 36(4) compliance check (provisional ITC limit) Day 75: Provisional ITC tracking

### Days 76-80 — Differential analysis, scorecard, UI, tests

Day 76: Find invoices in 2B not in books Day 77: Find invoices in books not in 2B Day 78: Vendor scorecard (% filed on time, historical) Day 79: GST Recon dashboard UI Day 80: Tests for reconciliation engine

## Weeks 17-18: Workflow Integration

### Days 81-85 — GSTR-3B prep, follow-up workflow

Day 81: GSTR-3B preparation helper (eligible ITC summary) Day 82: Eligible vs ineligible ITC categorisation Day 83: Email vendor about late filings — template + API Day 84: Follow-up workflow UI (track status of vendor follow-ups) Day 85: ITC at-risk dashboard (CFO view)

### Days 86-90 — Trends, integration, launch

Day 86: Historical trend visualization (your ITC compliance over time) Day 87: Integration with TDS check (cross-reference vendor data) Day 88: GST Recon as close period task Day 89: End-to-end GST recon tests Day 90: Phase 3 launch + customer email + pricing announcement

# Phase 4 — Tally Live Sync (Days 91-130)

Goal: Desktop agent that auto-pulls Tally data. Moves AIQL from monthly to daily product.

Prerequisites:

- Tally TDL expertise (you learn it Weeks 17-18, or hire specialist)

- Code signing certificates (Windows + Mac) — ~₹15K + ₹10K

## Weeks 19-21: Desktop Agent

### Days 91-100 — Agent foundation

Day 91: Agent architecture design (Tauri vs Electron decision) Day 92: Tauri setup + cross-platform skeleton Day 93: Windows agent skeleton (system tray, settings, status) Day 94: Mac agent skeleton (menu bar, settings, status) Day 95: TDL/XML data extraction from Tally HTTP endpoint Day 96: Voucher extraction Day 97: Master data extraction (vendors, customers, accounts, GSTINs) Day 98: Delta detection logic (last sync timestamp, change tracking) Day 99: Local SQLite cache for sync state Day 100: Local PII tokenisation (agent strips PII before cloud upload)

### Days 101-105 — Cloud sync, installer

Day 101: Tokenisation key management (key generation, secure storage in OS keychain) Day 102: Cloud sync endpoint (receive deltas from agent) Day 103: Sync state reconciliation (handle conflicts) Day 104: Windows installer (MSI build pipeline) Day 105: Mac installer (pkg build pipeline)

## Weeks 22-23: Sync Pipeline

### Days 106-115 — Scheduling, resilience, status

Day 106: Scheduled sync (cron-based daily at user time) Day 107: On-demand sync trigger (from agent menu) Day 108: Conflict detection logic Day 109: Conflict resolution UI (manual review) Day 110: Network resilience — retry with backoff Day 111: Network resilience — offline mode (queue locally) Day 112: Sync status dashboard (cloud-side view of agent health) Day 113: Sync error reporting + alerting Day 114: Agent metrics + telemetry (privacy-preserving) Day 115: Tests for sync pipeline

## Weeks 24-25: Real-time Workflow

### Days 116-125 — Notifications, alerts, integration

Day 116: Auto-trigger scan on new data sync Day 117: Notification system (email + in-app) Day 118: Critical finding alerts (immediate) Day 119: WhatsApp digest integration (via Gupshup or Twilio India) Day 120: Anomaly alerts — configurable thresholds Day 121: Alert subscription management (per user, per type) Day 122: Slack integration (optional) Day 123: Email digest builder (daily/weekly) Day 124: Tests for notification system Day 125: Audit trail of syncs

## Week 26: Polish + Launch

### Days 126-130

Day 126: Windows code signing (EV certificate) Day 127: Mac notarization (Apple Developer ID) Day 128: Auto-update mechanism (electron-updater or Tauri equivalent) Day 129: Agent documentation for IT teams (installation guide, firewall rules) Day 130: Phase 4 launch + customer email + pricing announcement + celebration

# Templates & References

## Sonnet prompt template (use for any day)

[Context section]
Read these files first to understand the codebase:
- {specific file paths from the day's entry}

[Task section]
[Copy the day's implementation notes + acceptance criteria]

[Verification section]
Before declaring done:
1. Run pnpm typecheck
2. Run pnpm test (or pnpm --filter {package} test for scoped)
3. Manually verify the acceptance criteria
4. Update CLAUDE.md if architecture changed

[Constraints]
- Use existing patterns and components — don't introduce new conventions
- Add new code in the appropriate package — don't put backend logic in apps/web
- Follow the existing test patterns (vi.hoisted for mocks, etc.)
- All tests must pass before marking complete

## Weekly review checklist

Every Friday afternoon (30 minutes):

- What shipped this week vs plan?

- Any spillover to next week?

- Tests still all passing?

- Production stable (Sentry dashboard)?

- Any customer feedback to incorporate?

- Next week's day-1 prompt ready in advance?

## When to deviate from the plan

Acceptable reasons to skip/swap a day:

- Customer urgently needs a feature not on the plan (bug fix, integration request)

- A planned feature reveals a deeper architectural issue that needs addressing first

- Phase 1 features need to ship faster than planned for an upcoming demo

Not acceptable reasons:

- "I don't feel like building X today"

- "Y looks more interesting"

- "Let me build the agent workflow instead"

The plan succeeds only if executed in order. Variations compound — by month 3, off-plan work means you've shipped a different product than designed.

## Tracking sheet template

Maintain a simple Google Sheet:

| Day | Date | Title | Status | Hours | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | 2026-06-02 | Demo loader UI | Done | 4 | All criteria met |
| 2 | 2026-06-03 | Onboarding step 1 | In progress | 6 | Spillover 1 day |
| ... |  |  |  |  |  |

Update daily. Review weekly. Plan monthly.

# Final Notes

## What this plan delivers

After 130 days:

- AIQL is feature-complete for Indian SME finance teams + CA firms

- Pricing genuinely defensible at ₹2,499 / ₹5,999 / ₹11,999

- 30-60 paying customers (parallel customer acquisition runs)

- Real moat: workflow integration (GSTN, Tally, Bank Recon) + knowledge base data

## What it doesn't deliver

These come LATER (Year 2):

- ISO 27001 / SOC 2 certifications

- Mobile native app

- Enterprise features (multi-org, BYOK encryption, dedicated support)

- International market features

- Banking / lending verticals

## The critical reminder

This is a 6-month engineering plan. It doesn't include customer acquisition work — which is at least equal in time and importance. Use the separate Sales Playbook (AIQL_SALES_PLAYBOOK.pdf) for that.

Engineering without customers = expensive prototype. Customers without features = unsustainable promises. Both must happen in parallel.

Plan generated May 30, 2026. Revise quarterly based on actual progress and customer feedback.